## Sheet1
Smart Meter Installation Communications Plan
NOTE: Materials listed in the comment boxes are available on Cooperative.com
Audience | 3-6 months Out | 3 months to 6 weeks out | 1 week out from first installation | Installation | Follow up
Employees and board members | • all-staff briefing (Powerpoint) • Board meeting (Powerpoint) • Begin training CSRs on how to work with the customer to understand the new bill information and address complaints. | • article in the employee newsletter • equip staff with information cards • post information, including FAQ, on your intranet |  |  | • Get feedback from CSRs on the calls that have been coming in.
Stakeholders (community leaders, government agencies, media) | • send letters to stakeholders • hold meetings with stakeholders (Powerpoint) • seek invitations to community and civic organization meetings | • issue press advisory and release | • media interviews
Consumer members | • Article in the newsletter or other communications to members | • publish article in the consumer-member newsletter • send letter to all consumers • include informational bill insert or, for on-line billing, link to website information | • robo-call to members • email to members • letter to members • website page with FAQ • pre-installation bill insert or brochure • notice on co-op FaceBook page • Tweet | • Tweet progress of installations • post-installation door hangers | • newsletter updates on the installations
Note on B5: tkw0: 1) Powerpoint on the smart meter rollout
Note on C5: tkw0: Materials: 1) Powerpoint; 2) CRN publications; 3) employee newsletter article
Note on B7: tkw0: Materials: 1) stakeholder letter; 2) Powerpoint presentation; 3) brochure; 4) FAQ
Note on C7: tkw0: Press release
Note on B9: tkw0: Materials: Newsletter article
Note on C9: tkw0: Materials: 1) newsletter article; 2) consumer member letter; 3) bill insert
Note on D9: tkw0: Materials: 1) letter; 2) bill insert or brochure; 3) FAQ
Note on E9: tkw0: Material: 1) door hanger